## Improvements
R&S Lead OS — Six Improvements
From Claude's update on the live dashboard · Oct 1, 2026 · Tested on a copy of real data; not yet clicked through on the live version.
# | Improvement | What's included | Status | Notes
5 | Lead detail drawer | Opens from Leads and Approval Queue with list visible behind. Shows company (incl. city/county), primary contact, score + breakdown, Claude research, activity Found→Closed. Buttons: Approve, Reject, Research with Claude, Suppress, Add to Campaign, Open Website, Open LinkedIn. | Done | Add to Campaign greyed out until a sender is connected.
6 | Research with Claude | Button in Approval Queue and drawer; researches only the clicked company; saves business summary, likely cleaning need, personalization note, outreach angle, confidence. Drawer and queue update immediately. | Done | Uses only facts already on file (no web browsing); confidence capped at 60%. Ask Claude in chat for website-checked research. First click asks permission; uses your Claude allowance.
7 | Actionable DNS / domain / mailbox states | 'What needs fixing' section on Mailboxes & Domains: what's wrong, what happens next, a button for each. External actions open InboxKit and are labelled as such. | Done | 6 pending domains have no mailboxes, so InboxKit hasn't published their records. Adding mailboxes is a purchase. No invented provider controls.
8 | Needs Your Attention panel | Panel at top of Dashboard, blockers first, real data only, one action button per item. | Done | Current items listed on the 'Needs Attention' tab.
9 | Protect the main R&S domain | 'Primary Business Domain — Protected' badge; 'Scheduled for removal from InboxKit only' / 'Domain registration: Not affected unless independently confirmed'; excluded from mailbox rotation and campaign assignment; Suppress asks for confirmation. | Done | The dashboard has no buttons that delete or change domains/mailboxes, so nothing else needed a confirmation.
10 | End-to-end test tracker | Dashboard panel marking each step done / blocked / to do / not yet possible and naming the current blocker. | Done | The loop itself is not complete — see 'End-to-End Test' tab.
| Done | 6
| Total | 6

## End-to-End Test
End-to-End Test Status
Status values: Done · Blocked · To do · Not yet possible. Edit column C to update; the summary recalculates.
Step | Stage | Status | Detail
1 | Lead found | Done | 63 companies from Getlead
2 | Saved to Railway PostgreSQL | Blocked | Web app not deployed; data is in the dashboard's own database for now
3 | Deduplicated | Done | Duplicates merged by domain / company
4 | Scored | Done | 100-point score on every lead
5 | Claude researched | To do | Click Research with Claude on any lead
6 | Approved | To do | Approve any lead in the queue
7 | Sender connected | Blocked | No sending tool linked
8 | Email sent | Not yet possible | Needs a sender and your launch approval
9 | Reply synced | Not yet possible | Needs sent email
10 | Dashboard updated | Not yet possible | After replies sync
| Done | 3
| Blocked | 2
| To do | 2
| Not yet possible | 3
| % complete | 30%
| First blocker | Saved to Railway PostgreSQL

## Needs Attention
Needs Your Attention
Real, unresolved items as shown on the Dashboard, blockers first.
Priority | Severity | Item | Detail | Action button | External action?
1 | Blocker | Sender not connected | Approved leads can't be emailed; no sending tool is linked to InboxKit mailboxes, and Getlead can't send email. | Connect Sender | No
2 | Blocker | Confirm the primary domain change in InboxKit | rscentralvalleycleaning.com is scheduled for removal from InboxKit only. The domain itself is not deleted — confirm it was intended. | Review Domain | Yes — InboxKit → Domains
3 | Blocker | Railway deployment incomplete | PostgreSQL is provisioned; the web app is not deployed. | Finish Railway Setup | Yes — Railway
4 | Warning | 18 mailboxes not warming | New Google mailboxes need about 2–3 weeks of warmup before cold volume. | View Mailboxes | Yes — InboxKit or sender
5 | Info | 6 domains with pending DNS | No mailboxes on these yet, so InboxKit hasn't published their email records. | Fix DNS | Yes — InboxKit (paid to add mailboxes)
6 | Warning | 16 leads waiting for approval | Qualified leads with a verified decision maker. | Review Leads | No

## Next Steps
Next Steps
Things only you can unblock.
# | Step | What's needed | Where | Owner | Notes
1 | Railway deployment | Create a token in Railway under rs-lead-gen-os → Settings → Tokens and paste it to Claude. | Railway | You | Claude deploys the app and copies the dashboard's data into PostgreSQL.
2 | Email sender | Tell Claude which sending tool you want to allow. Your rules exclude Instantly and Smartlead; Getlead and InboxKit can't send email themselves. | Your decision | You | Tracker stays blocked at 'Sender connected' until then.
3 | Primary domain in InboxKit | Confirm the removal from InboxKit was intended. | InboxKit → Domains | You
4 | First research + approval | Click Research with Claude and Approve on a lead to move two tracker steps to Done. | Dashboard | You | First research click asks permission.